# 03 — The 60-Day Launch

## Timeline, Week 1 checklist, venue outreach, DJ lineup, bootstrap budget

## The Target

Event #1 — PULSE: The First Room

Where: Chicago (venue TBD, see shortlist below)

When: Saturday, June 2026 (exact date locked Monday — see Date Decision section)

Time: 2:00pm – 5:00pm (daytime, sober, summer light)

Room size: 40-50 people

Format: 2-3 DJs, Andrea hosts and curates, runs the room

Goal: Break even financially. Win emotionally. Capture stories.

## Date Decision (Lock on Monday)

⚠️ June 13-14 is out. That weekend lands on a major Chicago cultural event and we don't want to compete with it. Those are the dates the first version of this package used — scratch them.

Remaining June candidates. Each one needs a Chicago-cultural-calendar check before locking — a Monday call action for you or Andrea is to spend 5 minutes on Choose Chicago / Time Out Chicago / Do312 cross-referencing the top two picks.

| Date | Day | Runway | Pros | Watch-outs |
| --- | --- | --- | --- | --- |
| Saturday, June 6 | Sat | 56 days | Earliest, first clean summer weekend, no major known conflicts | Tight on IG content ramp — 8 weeks from zero followers is aggressive. Chicago Blues Festival historically falls early June; verify |
| Saturday, June 20 | Sat | 70 days | Longest runway, Father's Day weekend Saturday is actually ideal (people free Sat afternoon, family Sunday) | Verify no Juneteenth-weekend conflict; Father's Day proximity may affect Sunday-morning posts |
| Saturday, June 27 | Sat | 77 days | Deepest into summer energy | Chicago Pride Parade weekend — likely a hard no-go, the city is saturated with events |

My updated recommendation: Saturday, June 20. It gives the widest content runway, the Saturday afternoon slot doesn't actually conflict with Father's Day (Sunday), and it's the cleanest of the three pending your calendar check.

Backup: Saturday, June 6. Tight but doable. Only pick this if June 20 fails the cultural-calendar check.

Fallback (if all of June is compromised): Saturday, July 11. Pushes the sprint to ~90 days, which is actually better for content ramp — June being loaded might be a feature, not a bug. Keep this in your back pocket.

Monday action: I'll pull up the Chicago cultural calendar on the call and we cross-check June 20 and June 6 live. We lock one before we hang up.

## The 60-Day Timeline (Week by Week)

Each week has one theme and three deliverables. Nothing more. Focus is the product.

### Week 0 — **THIS WEEKEND (Apr 11-13)**

Theme: Receive, react, prepare.

☐  Andrea reads the full package, marks it up

☐  Andrea signs up for Claude ($20/mo)

☐  Farrice DMs cousin JR — early soft ask, no commitment yet

### Week 1 — **Apr 14-20** — *Foundation Week*

Theme: Lock identity, launch the account, open venue conversations.

☐  Monday call — decisions locked

☐  Instagram account live (@pulsechi or equivalent — handle check Monday)

☐  First post ships (see file 04)

☐  Venue outreach emails sent (5 venues, template below)

☐  Date confirmed with JR

☐  Ten-person invite list drafted (not sent yet)

### Week 2 — **Apr 21-27** — *Lock-In Week*

Theme: Get a venue handshake and begin warm outreach.

☐  Venue locked (or 2 finalists with site visits scheduled)

☐  Event date publicly announced on IG (post #2)

☐  First 10 invites sent personally (text, not DM)

☐  Second DJ slot confirmed (via JR's network or Andrea's)

### Week 3 — **Apr 28-May 4** — *Open Gates Week*

Theme: Soft-launch tickets to warm list.

☐  Eventbrite / Luma / Partiful page live (Luma recommended — cleaner gate)

☐  Warm list gets first-access link

☐  Post #3 ships (event details reveal)

☐  Third DJ slot confirmed (optional — or JR plays two hours)

### Week 4 — **May 5-11** — *Momentum Week*

Theme: Build public awareness without public tickets yet.

☐  First Reel ships (movement + founding story)

☐  Second Reel ships (Andrea's curation philosophy — the music-as-permission-slip angle)

☐  20/45 seats committed

☐  Venue walk-through done, logistics list started

### Week 5 — **May 12-18** — *Public Gate Week*

Theme: Open public applications with the "why" gate.

☐  IG post announcing public gate

☐  Applications processed daily

☐  30/45 seats committed

☐  First two Pulse couples' stories drafted (from Andrea's invited network — "people you think might spark at this event")

### Week 6 — **May 19-25** — *Story Building Week*

Theme: Make attendees feel like they're joining something.

☐  Post: "Who's coming" tease (no names, just vibe)

☐  Behind-the-scenes Reel (Andrea prepping, JR prepping)

☐  40/45 seats committed

☐  Photographer booked (or friend with a camera confirmed)

### Week 7 — **May 26-Jun 1** — *Close the Room Week*

Theme: Final 5 seats, final logistics, storytelling infrastructure live.

☐  Room is closed (45/45) or capped and waitlisted

☐  Exit interview script printed and practiced (see file 04)

☐  Day-of run sheet built

☐  Contingency plans (weather, no-show, venue issue)

### Week 8 — **Jun 2-8** — *Dress Rehearsal Week*

Theme: Run it like it's real. Break what breaks.

☐  Walk-through at venue with JR + sound check

☐  Andrea's opening speech rehearsed (90 seconds, memorized)

☐  All 45 attendees confirmed via text

☐  Final playlist sequencing locked with JR

### Week 9 — **Jun 9-15** — *Event Week*

Theme: Ship it.

☐  Thu: Last check-ins, attendee reminders

☐  Fri: Venue setup, playlist finalized

☐  Sat Jun 13 — PULSE: The First Room

☐  Sun: Recovery, debrief, first photos posted

## Week 1 Checklist (The Only Thing You Need to Look At Monday Morning)

This is the Fladlien-subtracted version. Every item has been tested against: "Can Andrea do this in under 2 hours this week without friction?" If no, it got cut.

| # | Action | Time | Who | By when |
| --- | --- | --- | --- | --- |
| 1 | Sign up for Claude Pro ($20/mo) | 5 min | Andrea | Mon before call |
| 2 | Reserve IG handle — @pulse.chi or next available | 10 min | Andrea | Mon on call |
| 3 | Set up IG profile (bio, pfp, first post) | 30 min | Andrea + Farrice | Mon on call |
| 4 | Ship Post #1 (see file 04) | 5 min | Andrea | Mon on call |
| 5 | Send 5 venue outreach emails (template below) | 45 min | Andrea | Wed Apr 15 |
| 6 | Text JR (via Farrice) to confirm DJ #1 slot | 5 min | Farrice → Andrea | Tue Apr 14 |
| 7 | Draft the 10-person invite list (private, not sent yet) | 30 min | Andrea | Fri Apr 17 |

Total time for Andrea this week: ~2 hours of actual work. Plus the Monday call.

That's it. If Andrea does nothing else this week, Pulse is still on track. Everything else is either Farrice's job or deferred to Week 2.

## The Venue Outreach Pack

### Five Chicago venue targets (research these Monday, refine shortlist together)

| # | Venue | Why it fits | Neighborhood | Notes |
| --- | --- | --- | --- | --- |
| 1 | Salvage One | Warm warehouse aesthetic, 10,000 sq ft, cinematic afternoon light through tall windows — looks like a Pulse room on Instagram | West Loop | Premium, but daytime weekend rates are gentler |
| 2 | The Dalcy | Industrial-chic, smaller rooms, can be configured for 50-person intimate | West Loop | Owned by 16" on Center — they understand events |
| 3 | Morgan Manufacturing | Raw industrial, big floor, less corporate than Salvage | West Loop | Site visit needed — sound system not always included |
| 4 | Emporium Arcade Bar — Logan Square (private room) | Neighborhood-embedded, has a sound rig, $0-low rental if you drive bar revenue | Logan Square | Negotiate drink-revenue-share model |
| 5 | Chop Shop / 1st Ward (Wicker Park) | Music venue already, sound system is the selling point, daytime slot is usually open | Wicker Park | Easiest sound setup, hardest aesthetic lift |

Backup tier (if the above 5 fall through):

Zhou B Art Center (Bridgeport) — gallery with event space, unusual lineage, premium feel

Mana Contemporary Chicago — art gallery with large open floors

Revel Motor Row — South Loop, historic, big capacity, but probably too big for Event #1

Sleeping Village — Avondale, music-bar, smaller daytime slot possibility

Park No. 571 (Promontory Point) — outdoor, free, weather-gated, could be a backup if venue falls through entirely

### The venue pitch email (paste this, customize the [brackets])

Subject: Chicago daytime dance event — Saturday June 20 — would love to explore partnership

Hi [Name],

I'm Andrea, a Chicago-based DJ launching a new event called Pulse. It's a daytime, sober, curated dance gathering for 40-50 people — designed for Chicagoans who are tired of dating apps and want to meet each other the old way, through music and movement.

I'm writing because [Venue Name] is one of the five spaces in Chicago where Pulse would make sense. [Specific reason: "Your space has the warm afternoon light and the room proportions I need for a daytime event that feels intimate but alive." OR "Your sound system is already what I'd need, and your daytime weekend slots are usually underutilized."]

The event:

Saturday, June 20, 2026, 2:00pm – 5:00pm

40-50 people, curated guest list, all sober (no alcohol served)

3 DJs, 3 hours, one intentional energy arc

Full production handled on our side

What I can offer:

Bar / drinks venue: Keep 100% of any non-alcoholic beverage revenue + flat venue fee or revenue share on tickets

Rental-model venue: Flat fee for a 4-hour window (2pm-6pm including setup)

Either way: I handle all marketing, guest management, setup, and teardown. Your space stays exactly how you left it.

Why this is different:

Pulse isn't a hookup night or a speed-dating mixer. The market research and cultural shift around anti-app, sober daytime events is strong — there's no one in Chicago running this exact format yet, and I want the first one to happen in a venue that understands music and design.

Could we set up a 15-minute call or site visit this week? Happy to work around your schedule.

Thanks,

Andrea

[phone] | [email] | [Instagram when live]

### Outreach rules

Send 5 on the same day. Not one-at-a-time. You want replies competing with each other, and you want to be comparing options when you pick.

Follow up in 48 hours if no reply. One follow-up, polite, brief.

Don't negotiate pricing over email. Get them on a call first. Everything is negotiable in person. Nothing is negotiable in writing.

Bring Farrice into any venue call that matters. I can be on the call silently or actively — whichever you want. Having a second set of ears catches details you'd miss.

## The DJ Lineup

### DJ #1 (Anchor): **JR** (Farrice's cousin)

JR is the anchor. Here's why this is a big deal:

He's a working Chicago DJ. He has momentum, a local audience, and network.

He can help curate the right first 20 attendees — he knows people who'd get it.

He brings his own sound check credibility. When you're pitching a venue, "I have a DJ with local pull" is different from "I'm a new DJ."

He's family. Family doesn't flake when the thing is still unproven. This matters in Week 1-3 when everything is fragile.

Action (Farrice will handle Tuesday):

I'll text JR Monday night or Tuesday morning with a warm intro ask. Framing:

"Yo, my wife's friend Andrea is starting a really cool daytime sober dance party thing in Chicago — we're launching the first one mid-June. It's gonna be small, curated, like 40 people, three DJs over three hours. I told her you'd be the first person I'd ask to anchor it. Can I connect you two? She'd love to talk."

Once JR is warm to it, I'll connect you both directly via text. From there you run the relationship — he's your DJ partner, not mine.

### DJ #2: **Andrea's network** (find this week 2-3)

We need one more DJ. Two options:

Option A (preferred): JR recommends someone from his Chicago circle who shares the Pulse ethos.

Option B (backup): Andrea asks her own DJ friends. Preferably someone who's not a club DJ — someone who knows how to read a room that isn't drunk.

Target: Lock DJ #2 by end of Week 2 (Apr 27).

### DJ #3 slot (optional): **Flex**

We don't strictly need three DJs. Two DJs doing 90-minute sets each is cleaner than three DJs doing rotating hours. Decision deferred to Week 3. Depends on whether JR wants to play a longer set, whether Andrea finds someone great, and how the energy of the event shapes up.

If there's no DJ #3, the final 30 minutes can be a closing set from JR or a curated playlist handoff. Either works.

### What JR is NOT

JR is not a partner in Pulse. He's the anchor DJ for Event #1. If Event #1 goes well, we talk about continued collaboration in Event #2. If Pulse grows, Andrea decides whether JR plays a role beyond guest DJ. No equity, no long-term commitments, no mission creep. One event at a time.

## The Bootstrap Budget

Goal: Net cost to Andrea = $0. Presell tickets cover production. Break-even is a win. Small profit is a bigger win.

### Costs (bootstrap mode — every line justified)

| Category | Item | Cost | Notes |
| --- | --- | --- | --- |
| Venue | Flat fee or rev-share | $0-300 | Target: $0 via rev-share deal |
| Sound | Venue provides OR JR brings | $0-150 | JR likely has his own rig |
| Lighting | Bring your own (string lights + warm bulbs from Amazon) | $50 | No uplighting needed for daytime |
| Photography | Friend with a camera + iPhones | $0 | Event #2 we hire someone |
| Decor | Candles, a few fabric pieces, flowers | $40 | Keep it minimal and real |
| Refreshments | Water, non-alcoholic canned drinks, simple snacks | $100 | Costco run |
| Printing | Welcome cards with timeline + consent | $15 | Staples same-day |
| Insurance | Event liability (one-off) | $70 | Required by most venues |
| Ticketing | Luma or Partiful | $0 | Both free for events |
| TOTAL |  | $275-625 | Target: under $400 |

### Revenue scenarios (using the tiered model from the research doc)

| Attendees | Mix | Revenue | Net (vs $400 cost) |
| --- | --- | --- | --- |
| 30 (low) | 10 @ $25 + 15 @ $35 + 5 @ $45 | $1,000 | +$600 |
| 40 (target) | 15 @ $25 + 20 @ $35 + 5 @ $45 | $1,300 | +$900 |
| 50 (full) | 20 @ $25 + 25 @ $35 + 5 @ $45 | $1,500 | +$1,100 |

Reality check: At 40 attendees and bootstrap costs, Andrea nets roughly $900. That's not a side-hustle number — that's real money for a first event. More importantly, it proves the unit economics work, which makes Event #2 venue conversations radically easier ("our last event sold out, here's the revenue, let's talk").

### The break-even line

12 tickets at $35 average covers all costs. That's the floor. If Andrea can sell 12 tickets (which is half of her own 20-person invite list), Event #1 does not lose money. That's the psychological baseline for her to hold through the nervous middle weeks.

### Andrea's up-front outlay

~$225 before first tickets sell. (Venue deposit if any, insurance, printing, initial supplies.) Every dollar after that comes from ticket revenue.

Monday action: Confirm Andrea is comfortable with ~$225 up-front exposure. If not, we restructure — there are ways to get it closer to $50 out-of-pocket by deferring venue deposits and skipping insurance (though insurance is strongly recommended).

## Your Action on This File

Pick your Event #1 date preference. June 20 is my rec. June 6 is the backup. July 11 is the fallback if June is compromised. Tell me Monday after we cross-check the cultural calendar live.

Scan the venue list. Do any of these stand out to you based on your own Chicago knowledge? Any you'd want to add or remove?

Confirm the ~$225 up-front budget. If that's a stretch, say so — I'll redesign it.

Look at the Week 1 checklist. Is there anything there that makes you say "ugh, I don't want to do that"? That's the one we need to talk about. Friction is data.

Monday we lock all of this. Everything downstream depends on it.