# 06 — Run-of-Show

Heart encounters, not head encounters — a daytime, sober dance party in Chicago for people who want to meet a partner. The mechanic is body-first: the music does the emotional labor so the people don't have to. The metric is couples, not followers.

The operational playbook. What Andrea does, when, and in what order — from 14 days before the event through 1 week after. Stress-tested for daytime. Distinct from `research/03-event-blueprint.md`, which is the in-room experience arc — this is the production layer beneath that.

## How To Use This Document

This is the production-side run-of-show — every task Andrea (or a curator-team member) executes from event-prep through post-event capture. The in-room experience arc (opening / warm-up / floor / closing) lives in research/03-event-blueprint.md (currently in evening voice — needs daytime port; flagged for B1 review).

Use this doc as a checklist. Skip nothing without naming why.

Time anchors:

T-14: Two weeks before

T-7: One week before

T-3: Three days before

T-1: Day before

T-0: Day of

T+0: Hour of

T+1d: Day after

T+7d: One week after

## T-14 — Two Weeks Out: Lock & Confirm

### Logistics

☐  Venue confirmed in writing (date, hours including setup + breakdown, capacity, any restrictions)

☐  Final attendee count target locked (50 cap for Event #1, 55 hard buffer)

☐  DJ lineup confirmed in writing (Andrea + JR or backup; set times; backline needs)

☐  Sound system spec confirmed (PA brand/model, monitors, DJ mixer, cable runs, power)

☐  Insurance / liability confirmed if venue requires

☐  Photography plan: who's shooting (real human, not contracted clichés), what's permitted (no flash on the floor)

### Curation

☐  Phase 1 invites sent (25 hand-picked); responses tracked in Notion

☐  Phase 2 referral-from-Phase-1 invites flowing

☐  Why-gate live for Phase 3 public seats (10 spots)

☐  Application reviews running — Andrea's 15-min daily window

### Communication

☐  Calendar invite drafted (private, not public IG yet)

☐  What-to-bring email drafted ("eat first, bring water, phones go away on the floor")

☐  Pre-event hype post drafted (post T-7)

### Materials

☐  Tickets / RSVP confirmations ready (digital — see 02-briefs/event-ticket.md)

☐  Floor plan for the room sketched (DJ booth, water station, exit-interview spot, coat area)

☐  Music set list drafted by Andrea (1-2 hour main floor + bridge tracks)

## T-7 — One Week Out: Public Push & Final Filter

### Public push

☐  Public IG post goes live announcing event (final 10 seats opening)

☐  Stories sequence: 4-6 stories building anticipation (use 02-briefs/ig-story.md)

☐  Newsletter / email goes out to opt-in list (if email channel is live)

☐  One-line response template ready for inbound DMs ("Application here: [link]. We're in T-7 push.")

### Curation closure

☐  Why-gate review batch: clear all pending applications within 48h

☐  Final hell-yes / decline notifications sent

☐  Waitlist activated (people who'd come if a slot opens — 5-10 names)

☐  If under 35 confirmed yeses, tighten to 40 attendees instead of padding to 50 (per 02-pulse-who.md Curation Ratio rules)

### Logistics

☐  Backup-DJ contingency confirmed (if JR is the anchor, who's plan B)

☐  Day-of timeline drafted with arrival times for DJ, photographer, helpers

☐  Day-of comms channel set (group text / Signal thread for the team)

## T-3 — Three Days Out: Final Confirmations

### Confirmations

☐  Each confirmed attendee gets the what-to-bring + what-to-expect email (already drafted T-14)

Doors open at [X] / floor opens at [Y]

Daytime — eat first

Bring water

Phones go away on the floor

Exit interview is voluntary, ~2 minutes, on the way out

☐  DJ + photographer + helpers confirmed for arrival time

☐  Venue confirms day-of contact + access timing

### Capacity check

☐  Where are we vs target? If <30 confirmed yeses with 3 days to go, the event proceeds at the smaller size. Don't pad. (Quality > fill is non-negotiable.)

☐  Walk-up / day-of waitlist policy decided: are we accepting any?

### Materials prep

☐  Exit interview question sheet printed / loaded on phone

☐  Permission cards (for permission-cleared quote use) printed

☐  Phone-stash setup decided (a labeled basket / a wall hook system)

☐  Water station gear gathered (pitchers, cups, water; sliced fruit if budget allows)

☐  Welcome / mood signage drafted (if any)

### Andrea's prep

☐  Final music run-through — Andrea plays the full set in order, listens for transitions

☐  Day-of outfit decided (Andrea's body language carries the room — comfort + presence > style)

☐  Sleep plan: a real night T-2 (no late-night work the night before is non-negotiable)

## T-1 — Day Before: Quiet Day

### What does NOT happen the day before

No new DM responses to attendees beyond confirmations

No last-minute additions to the invite list

No unfinished setup pushed to morning-of

No social media engagement spirals

### What does

☐  All physical materials at the venue (or Andrea's car ready to load)

☐  DJ gear tested or pre-prepped (USB drives prepped, set list saved with backups)

☐  Andrea reviews 05-ops/03-drift-signals.md once — anchoring before show day

☐  Andrea reviews 05-ops/04-success-metrics.md once — what success looks like tomorrow

☐  Andrea reviews 00-foundation/05-non-negotiables.md — the lines hold

☐  Eat well, sleep well, no caffeine after 2pm

## T-0 — Day Of: Production Timeline

### Morning (T-0 minus 6 hours)

☐  Final venue walk-through if access permits

☐  Sound check + DJ rig setup (90+ min before doors)

☐  Floor plan executed: DJ booth, water station, exit-interview spot, coat area, phone stash

☐  Lighting check — daytime light should be the lead; no club lighting unless natural light fails completely

☐  Photographer briefed (no flash on the floor, no posed shots, capture moments not setups)

### Pre-doors (T-0 minus 30 min)

☐  Andrea + curator team in the room together for a 5-min huddle:

Anyone got a tag-out / I-need-air signal? (decide one — used if anyone needs a break)

Any specific names to watch (a Phase 3 admit who Andrea's slightly unsure about)

Confirm exit-interview rotation

☐  Music starts soft — pre-room ambient set, no floor songs yet

☐  Water station fully stocked

☐  Phone-stash signage visible at door

### Doors open (T-0)

☐  Andrea greets every arriving attendee personally if possible (curated room — the founder welcoming sets the posture)

☐  Phones to the stash at the door (warm, friendly, non-negotiable). One curator stationed here for the first 30 minutes.

☐  Room-warming music continues — not yet floor songs. Let people arrive into a held space, not a party already going.

### Floor opens

☐  Andrea moves to the booth at the announced time (or when the room feels ready — Andrea's call)

☐  First track is the room-shifter — the song she's been holding in her head for weeks for this exact moment

☐  No announcements from the booth other than Andrea welcoming the room briefly (30 seconds max — she's not the focus, the room is)

### Mid-event (T+0 minus 1 hour from end)

☐  Andrea reads the room. Energy peaking? Lulling? She's already got her "if it's lulling" track in queue.

☐  Curator team scans for anyone hugging walls, anyone on their phones (tap them, ask if okay), anyone who looks like they're checking out emotionally

☐  Photographer captures candid moments — never posed groups, never staged "look at the camera"

### Last 30 minutes

☐  Andrea drops the closer track — the song she's chosen as the emotional anchor of the night

☐  Slow-dance moment if it fits (3-5 min track that lets everyone breathe together one last time)

☐  Soft transition to the exit / wind-down

### Doors close (T+0 + event duration)

☐  Floor music ends; room music transitions to ambient

☐  Exit interview station active (Andrea + 1 curator running)

☐  Phones returned at door

☐  Last attendees out with thanks

### Breakdown

☐  DJ gear pack-up (Andrea or assigned helper)

☐  Materials gathered, water station broken down

☐  Final photographer dump (raw files to Andrea or Farrice)

☐  Venue cleared per agreement

## T+1d — Day After: Capture Window

The 24 hours after the event are when the data is freshest. Don't sleep on this.

### Before noon T+1

☐  Andrea voice-memos her gut read of the night (raw, before social input distorts) — sent to Farrice

☐  Exit interview answers transcribed from voice memos / notes into the Notion debrief database

☐  Photo dump reviewed; 5-8 strongest images flagged for content (real moments, not staged)

### Afternoon T+1

☐  Per-event debrief written (one page) following 05-ops/04-success-metrics.md:

Did each metric hit floor / target / miss?

Stories captured (verbatim quotes with permission tags)

Drift signals fired during the event?

What worked / didn't work

☐  Andrea texts/DMs the 5-10 attendees who showed up most lit ("thanks for being in the room — what stayed with you?") — captures more data + builds the relationship

### End of T+1

☐  Notion database updated: applications → outcomes (did they show? did they make a connection? do they want to come back?)

☐  Quote bank updated with permission-cleared quotes from exit interviews

☐  Andrea's voice memo + Farrice's processing turn the day's data into a per-event memo for the BOS update cycle

## T+7d — One Week After: Content Cycle + Reflection

### Content cycle

☐  First post-event IG post goes live (real photos, real quote with permission, real moment)

☐  Newsletter (if live) goes out with story-driven recap

☐  First "thank you" round to attendees (text, not mass email — feels personal because it is)

### Strategic reflection

☐  Andrea + Farrice review the per-event debrief

☐  Drift signals readback: did anything fire that wasn't named in the debrief?

☐  Pattern check: how does this event compare to prior events on the metrics?

☐  Decisions captured: what changes for Event +1 based on what we learned?

☐  Update relevant BOS docs (per Constitution principle: amend, don't rewrite — and only Andrea-named amendments)

### Application flow for Event +1

☐  Event #2 invite codes shared with Event #1 hell-yes attendees first (70% of next event's seats per Curation Ratio rules — see 03-marketing/04-curation-mechanics.md)

☐  Why-gate stays live; waitlist re-evaluated

## Critical Failure Modes (And Real-Time Triage)

### Failure 1: A Hunter or Drunk Group slipped through curation

Real-time response:

Don't escalate publicly. Pull aside the curator with the cleanest read.

Give them one warm, firm message: "This isn't quite the right room. We'd rather refund you than have you uncomfortable here."

Walk them out. Refund processed within 24h.

Per 03-marketing/05-crisis-comms.md Section "Hunter Slipped Through" for full protocol.

### Failure 2: DJ cancels last-minute

Triage:

Andrea takes the full set if needed (she's prepared a 3-hour solo set as backup — non-negotiable prep item).

Or: Farrice taps the DJ Homies network for a same-day fill-in.

Communication to attendees: only if the lineup was a draw (e.g., JR was named). If it wasn't named publicly, no announcement needed.

### Failure 3: Venue issue (lockout, AC failure, sound issue)

Triage:

Backup venue (if any) was identified at T-14.

Refund + reschedule communication template ready (drafted at T-7 as contingency).

Keep attendees informed within 30 min of any issue — silence breeds rumors.

### Failure 4: Attendance falls below 30

This is fine. Do not pad.

Quality at 25 beats fill at 50.

The room's energy is a function of curation, not headcount.

Use the night to over-document — 25 well-curated attendees produce more proof than 50 mixed ones.

### Failure 5: Energy lulls and the floor empties

Read the room:

Drop the "if it's lulling" backup track (Andrea has this in queue every event)

Curator team brings water, smiles, moves bodies on the floor (not commanding, just being present)

Sometimes a 4-minute reset (slow track, room takes a breath) is the best move

Don't panic-build to a peak. The room finds its rhythm if you trust the curation.

## What Andrea Doesn't Do During the Event

Doesn't post to social media live during the event (drift signal #1 — watching followers more than the floor)

Doesn't carry her phone on the floor (phones are off the floor — non-negotiable applies to the founder first)

Doesn't try to introduce people who haven't found each other on their own (the floor is the protocol; no forced introductions)

Doesn't give running commentary from the booth (Andrea is the curator, not the host of a wedding)

Doesn't apologize if something glitches (warm acknowledgement + move forward; apology destabilizes the room)

## Why This Document Exists

A3's diagnostic flagged the operational ops layer as one of the biggest gaps. Without a run-of-show, "Andrea curates the room" stays vague — she carries the entire event in her head, which is a founder bus-factor risk and a scaling ceiling.

This doc encodes the playbook. Per-event, it gets refined. By Event #5, the run-of-show is the curator-training document.

## Pre-Flight Checklist (Print This, Use This)

T-14 / T-7 / T-3 / T-1 / T-0 / T+1d / T+7d

Each phase has a critical-path item that, if missed, the event slips:

T-14: venue confirmed in writing

T-7: public push live

T-3: every attendee notified (what to bring, what to expect)

T-1: quiet day, sleep

T-0 morning: sound check + room set

T-0 doors: Andrea greets every arrival

T+1d: debrief written

T+7d: content live + Event +1 invites flowing

If any critical-path item slips, name it in writing and decide whether to delay the event.